## 工作表1
Moreandmall Project Schedule
Item |  | Content | Date
1 | Seller Upload Products | Add Products and send Email to Administrator Edit Delete Products Administrator approval Products Pay for COD Show products | 3 days (9 June- 11June)
2 | Search Products |  | 1days (12June)
3 | Member | Seller and Buyer Register Seller and Buyer Login Seller and Buyer Forget Passord Seller view buy record | 1days (15 June)
4 | News | Add,Edit,Delete news Show and Search news | 1days (16June)
5 | Paypal |  | 1 (17June)
6 | FAQ HOME ABOUT US CONTACT US FAQ |  | 1days (18June)